# Electric Vehicle Charging Infrastructure (EVCI) Trial

Site Portfolio Report

22 October 2026

Table of Contents

Executive Summary	2

Project background	3

About this report	4

Site selection methodology	5

A portfolio approach	5

What makes a suitable site	5

How sites were identified and assessed	6

An iterative, multi-stage process	6

Assessment against Condition 6	8

Network constraints and demand-management learning	8

Diverse council engagement	8

High potential for EV charging load	10

Sites not subject to a current third-party connection request	10

Overall portfolio balance	10

Appendix A: Final EVCI site listing	11

# Executive Summary

This report sets out the final list of sites for the CitiPower, Powercor and United Energy (CPU) Electric Vehicle Charging Infrastructure (EVCI) Trial, together with the evidence supporting their selection. It is published in accordance with Condition 6 of the Australian Energy Regulator’s (AER) ring-fencing waiver decision, which requires CPU to publish its final EVCI sites and demonstrate that they appropriately balance four considerations.

The final portfolio comprises 100 sites across 12 local government areas, spanning inner-city, suburban, coastal and regional communities across the CPU distribution networks. 75 sites are in metropolitan Melbourne and 25 are in regional Victoria.

The portfolio has been designed so that, taken together, the sites deliver the learnings the trial was established to generate:

- Network constraints: of the 63 sites with a completed low-voltage network assessment, 30 have an identified voltage-drop or cable-capacity constraint. These sites will test how managed charging can operate where network headroom is limited, while unconstrained sites provide a point of comparison.

- Diverse council engagement: CPU engaged with 30 councils, of which 12 are participating. Participants range from inner-city municipalities to rural shires, each with different planning approaches, parking arrangements and community expectations.

- High potential for EV charging load: sites are located near shops, transport hubs, sporting facilities, tourist destinations and higher-density housing where many residents cannot charge at home.

- No current third-party connection requests: every site has been checked against CPU’s connection records to confirm it was not the subject of a current third-party connection request at the time of assessment, so the trial does not compete with private charging proposals.

# Project background

Victoria has set ambitious decarbonisation targets, including a commitment to achieve net zero emissions by 2045 and a long-term vision for zero-emission vehicles to become the dominant form of transport across the state.

A key enabler of this transition is the availability of reliable, accessible and affordable charging infrastructure. While electric vehicle adoption continues to grow, charging accessibility remains one of the most significant barriers influencing customer confidence and purchasing decisions.

Research consistently identifies charging availability, convenience and concerns regarding charging access as important factors affecting EV adoption rates. These challenges are particularly pronounced for customers who do not have access to private off-street parking, customers living in higher-density urban environments, and customers located in regional communities where charging infrastructure may be less prevalent.

Recognising these challenges, CitiPower, Powercor and United Energy developed the EVCI Trial to explore how existing electricity distribution infrastructure could support the delivery of public charging services in a safe, efficient and scalable manner.

The trial was established following a ring-fencing waiver application to the AER, enabling the networks to own, install and maintain EV charging infrastructure while independent third-party operators provide customer-facing charging services.

The trial is intentionally limited in scope and scale. It is designed as a learning initiative rather than a commercial charging network. The objective is to gather practical insights that can assist governments, regulators, network businesses and market participants in understanding how public charging infrastructure may evolve as EV adoption accelerates.

The trial focuses on several key areas:

- the impact of EV charging on demand in local networks

- the impact of customer charging on price elasticity during periods of both low and high demand

- the application of new technologies on the networks

- utilisation rates across different local area types, for instance residential streets compared with commercial and no-off-street-parking locations, to inform demand forecasting

- the impact of customer charging behaviour on network power quality

- the development of processes and technical guidelines for EVCI connections.

Representatives from CitiPower, Boroondara Council, participating eMSPs and other project partners at the launch of the first charger

# About this report

Condition 6 of the AER’s waiver decision requires CPU to identify the specific EVCI sites for its trial consistent with the following approach:

“a) within 12 months of this AER decision, publish on CPU’s website(s), and notify the AER of its publication, a listing of the final EVCI sites, with supporting evidence, demonstrating that these selected sites appropriately balance:

i) locations where there are network constraints, which ensure greatest learnings about demand management to address network constraints

ii) diverse council engagement

iii) high potential for EV charging load

iv) sites that are not subject to a current connection request by a third-party.”

This report is that listing. It explains how sites were identified and assessed, summarises how the portfolio as a whole meets each of the four considerations, and provides site-by-site evidence in Appendix A.

The information in this report reflects the site-selection evidence held by CPU at the date of publication.

James Kleine (zuup) showing CPUs General Manager Regulation and

General Manager Corporate Affairs, Customer and Strategy charging information on the zuup app

# Site selection methodology

## A portfolio approach

The final EVCI sites were assessed against the four considerations in Condition 6: network constraints and the opportunity for demand-management learning, diversity of council engagement, potential EV charging load, and whether a site is subject to a current third-party connection request.

The assessment considers both individual site characteristics and the collective balance of the final portfolio. The criteria have not been treated as equally weighted requirements that every site must meet to the same degree. A site in a constrained part of the network, for example, may have more modest, expected utilisation, while a busy tourist location may sit on an unconstrained part of the network.

## What makes a suitable site

Alongside the four Condition 6 considerations, CPU applied a consistent set of practical site-selection principles to every potential location (Figure 1). Together they aim to place chargers in prominent, not premium locations: easy to find and convenient for the people who need them, without taking the most sought-after parking in a street or shopping strip.

- EV uptake. Areas with high EV ownership, where demand for public charging is likely to emerge first.

- Off-street parking. Areas where many residents have limited off-street parking and cannot easily charge at home.

- Access to facilities. Locations close to amenities, parks, walking tracks, shopping, and cafés and restaurants, so drivers can charge while they go about their day.

- Network suitability. Poles that are physically suitable to host a charger, with electrical capacity assessed to determine the charger configuration and the learning the site can provide.

These principles map directly to Condition 6. Network suitability informs the assessment of network constraints, while EV uptake, off-street parking and access to facilities together indicate a site’s potential for EV charging load.

Figure 1: CPU’s EVCI site selection principles

## How sites were identified and assessed

Sites were developed through the following steps:

- Council engagement. CPU engaged with councils across its three networks. Participating councils helped identify suitable kerbside locations, drawing on their local knowledge of parking demand, streetscape and community needs. Some councils contacted CPU proactively to take part.

- Potential site identification. Potential sites were identified by councils, CPU and by customers (via our dedicated engagement page), with a focus on locations near existing poles where residents and visitors are likely to need public charging. Sites identified by CPU are labelled “CPU selected” in Appendix A.

- Network assessment. CPU’s technical leads assessed the low-voltage network at each potential site, including available supply capacity, voltage-drop risk and cable capacity, to classify the site and identify the learning it would provide.

- Charging-load assessment. Each site was reviewed for the local features that drive charging demand, such as nearby shops and services, transport, sport and recreation facilities, tourism, and the share of housing without off-street parking.

- Third-party connection check. Each site was checked against CPU’s connection records to confirm it was not the subject of a current third-party connection request. The outcome of each check is recorded in Appendix A.

- Portfolio review. The shortlisted sites were reviewed together to confirm that the final portfolio achieves an appropriate balance across the four considerations.

## An iterative, multi-stage process

While CPU collectively operates more than 800,000 poles across its networks, the number of poles that can practically support public EV charging is substantially lower. Site suitability depends on a range of factors, including network configuration and available capacity, technical and engineering constraints, proximity to suitable parking bays, accessibility requirements and local planning considerations.

Site selection has therefore not been a linear process. Sites that initially appeared suitable were in some cases excluded because of engineering constraints, parking considerations, council feedback, community concerns or changing operational requirements. The trial has shown that the presence of a pole alone is not a reliable indicator of suitability, and that several rounds of assessment and refinement are often needed before a viable site is confirmed.

More than 856 potential sites have undergone detailed assessment, and over 744 of these progressed to council review. The final portfolio of 100 sites therefore represents fewer than one in eight of the locations assessed.

This level of attrition reflects the care taken to balance technical feasibility, customer demand, parking, local amenity and stakeholder views. It also means that council and community input has directly shaped the final portfolio: locations were removed or refined where local feedback indicated they were not appropriate.

The experience reinforces the importance of maintaining a large pipeline of potential sites, and of ongoing collaboration between distribution networks, councils and communities. Any future large-scale deployment program should expect significant attrition through assessment and approval, and plan its targets, timelines and resources accordingly.

# Assessment against Condition 6

## Network constraints and demand-management learning

Understanding how EV charging interacts with a constrained local network is one of the most valuable learnings the trial can offer, because these are the conditions under which networks most need to manage demand efficiently. Of the 63 sites with a completed low-voltage network assessment, 31 (49%) have an identified voltage-drop or cable-capacity constraint, and a further three have limited supply capacity that has determined the charger configuration. Constrained sites are spread across both metropolitan and regional networks, from inner Melbourne to Birregurra, Beeac, Forrest, Elmore and Warrnambool.

Table 1: Network classification of final EVCI sites

| Network classification | Sites | Learning opportunity |
| --- | --- | --- |
| Voltage-drop constraint | 10 | Tests whether managed or reduced charging rates can keep customer voltages within limits without network augmentation. |
| Cable-capacity constraint | 7 | Tests how charging load can be managed within the thermal limits of existing cables, including the use of single-port chargers. |
| Voltage-drop and cable-capacity constraints | 14 | Provides the most demanding test of demand management where both limits apply. |
| Limited supply capacity (no constraint at installed load) | 3 | Demonstrates how charger configuration can be matched to available capacity. |
| Supply available – no network constraint | 32 | Provides a comparison point for utilisation and network impact where supply is not limited. |
| Not assessed for network constraints | 33 | Contributes learnings on charging behaviour, utilisation and broader demand management. |
| Assessment not yet complete | 1 | Assessment to be completed. Includes one site (Gellibrand) where circuit cable details are unknown. |
| Total | 100 |  |

At a number of constrained sites, CPU has deliberately connected chargers at a load that will test the limits of the local network. These sites will show how charger configuration and demand management can unlock public charging in locations that would otherwise require network upgrades.

## Diverse council engagement

The trial involves 12 councils with very different characteristics. They include dense inner-city municipalities where most residents rely on kerbside parking, established and growing suburban councils, coastal and tourism-focused shires, and regional cities and rural towns. This range allows the trial to test approvals, parking management and community engagement processes across the kinds of councils that will be involved in any wider roll-out of kerbside charging.

Table 2: Participating councils

| Council | Setting | Sites |
| --- | --- | --- |
| City of Yarra | Metropolitan | 25 |
| City of Boroondara | Metropolitan | 17 |
| Glen Eira City Council | Metropolitan | 13 |
| Frankston City Council | Metropolitan | 7 |
| Kingston City Council | Metropolitan | 7 |
| Mornington Peninsula Shire | Metropolitan – coastal | 6 |
| Colac Otway Shire | Regional | 7 |
| Campaspe Shire Council | Regional | 5 |
| City of Greater Bendigo | Regional | 5 |
| Moorabool Shire Council | Regional | 5 |
| Warrnambool City Council | Regional | 2 |
| Horsham Rural City Council | Regional | 1 |
| Total |  | 100 |

Council engagement has also been diverse in nature. Some councils, such as the City of Yarra, came to the trial with established EV processes and a strong readiness to participate, while others, such as Campaspe Shire Council, approached CPU proactively to bring charging to their communities. Councils such as Glen Eira City Council and Kingston City Council have highly supportive officers championing the trial, with broader internal departments and management needing to be brought along the EV journey.

CPU’s engagement was not limited to the councils where EV chargers have been or will be installed. In total, CPU engaged with 30 councils across its three networks, spanning inner-city, suburban and regional communities. Eighteen of these councils did not proceed to sign a legal agreement and lock in preferred trial sites. They are listed in Table 3.

Table 3: Councils engaged who did not proceed

| Council | Setting |
| --- | --- |
| City of Melbourne | Metropolitan |
| City of Port Phillip | Metropolitan |
| Merri-bek City Council | Metropolitan |
| Ararat Rural City Council | Regional |
| Buloke Shire Council | Regional |
| Central Goldfields Shire Council | Regional |
| City of Ballarat | Regional |
| City of Greater Geelong | Regional |
| Corangamite Shire Council | Regional |
| Gannawarra Shire Council | Regional |
| Hepburn Shire Council | Regional |
| Loddon Shire Council | Regional |
| Macedon Ranges Shire Council | Regional |
| Mildura Rural City Council | Regional |
| Mount Alexander Shire Council | Regional |
| Pyrenees Shire Council | Regional |
| Surf Coast Shire Council | Regional |
| Swan Hill Rural City Council | Regional |
| Total | 18 |

Council non-participation was primarily driven by differing strategic priorities, varying levels of maturity in EV and sustainability planning, challenges in applying existing council approval processes to a new AC pole-mounted charging model, and concerns regarding liability and risk allocation. These factors demonstrate some of the practical institutional and governance barriers associated with introducing new public EV charging models.

## High potential for EV charging load

Sites have been chosen where communities are most likely to need and use public charging. The local features that drive charging demand are recorded for each site in Appendix A. Across the portfolio, they fall into several groups:

- Higher-density housing without off-street parking. Many inner-city sites in Yarra, Boroondara and Glen Eira serve terrace and apartment residents who cannot install a home charger, which is the group the trial most needs to understand.

- Shopping strips and activity centres. Sites close to local shops, cafés and services support “top-up” charging while people go about their day.

- Transport hubs. Sites near train stations, such as Colac and Cheltenham, support commuters who park for the working day.

- Sport and recreation. Sites near ovals, parks and reserves see regular evening and weekend visits.

- Tourism and travel routes. Sites along the Great Ocean Road, the Murray River, the Mornington Peninsula and regional highways support visitors and travelling motorists, and test seasonal patterns of demand.

- Regional black spots: Regional communities without any public chargers have welcomed our program to fill black spots.

Together these provide a cross-section of residential, destination and en-route charging, giving the trial an evidence base for forecasting demand in different local settings.

## Sites not subject to a current third-party connection request

Every site has been checked against CPU’s connection records to confirm that it was not the subject of a current connection request by a third party when assessed. This safeguard ensures the trial does not take up locations that a private charge point operator is seeking to develop.

## Overall portfolio balance

The final EVCI site portfolio has been assessed against the four considerations in Condition 6. Individual sites contribute differently to each consideration, but collectively the final locations provide opportunities to generate learnings about EV charging and demand management under differing network conditions, provide diversity in council engagement, include locations with high potential for EV charging load, and have been confirmed as not subject to a current third-party connection request. CPU considers that the portfolio appropriately balances the four considerations.

# Appendix A: Final EVCI site listing

The table below lists each final EVCI site with the supporting evidence for each Condition 6 consideration. The “High potential for EV charging load” column describes the local features expected to drive charging demand at each site.

Table 4: Final EVCI sites and supporting evidence

| Site number | Final EVCI site | Council | Network constraints & demand-management learning | Diverse council engagement | High potential for EV charging load | Third-party connection request | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Opp 20 Parkhill Rd Kew | City of Boroondara | Supply available – no network constraints Substation: BELMONT-PARKHILL Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Established residential street close to Kew Junction shopping, cafés and services | Site not subject to third-party connection request when assessed | In service |  |
| 2 | 2 Highfield Gr Kew 3101 | City of Boroondara | Supply available – no network constraints Substation: HIGH 79-HIGHFIELD (R) Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Outside apartment building - Supports apartment residents who cannot install home charging - Walkable to local shops and public transport | Site not subject to third-party connection request when assessed | In service |  |
| 3 | Opp 74 Banool Rd Balwyn 3103 | City of Boroondara | Supply available – no network constraints Substation: BANOOL-HERTFORD (R) Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to parks - Short trip to Balwyn village shopping and dining on Whitehorse Road | Site not subject to third-party connection request when assessed | In service |  |
| 4 | Opp 8 Robert St Balwyn 3103 | City of Boroondara | Voltage drop issues identified to add any load. Very high circuit demand (257kW) Substation: FRANK-ROBERT Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to sporting facilities - Weekend and evening sport generates regular visitor turnover - Near Balwyn village shops and cafés | Site not subject to third-party connection request when assessed | In service |  |
| 5 | Pretoria St Deepdene 3103 | City of Boroondara | Cable capacity issues identified to add any load. Very high circuit demand (191kW) Substation: BARNSBURY-WHITEHORSE Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Residential catchment close to Whitehorse Road shops and local parkland | Site not subject to third-party connection request when assessed | In service |  |
| 6 | 1A Chatfield Rd Deepdene 3103 | City of Boroondara | Supply available – no network constraints Substation: CHATFIELD-PARKSIDE Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to sporting facilities and school - School and sport activity supports both daytime and evening use | Site not subject to third-party connection request when assessed | In service |  |
| 7 | Opp 57 Denham St Hawthorn 3122 | City of Boroondara | Voltage drop issues identified to add any load. High circuit demand (207kW) Substation: DENHAM-BARTON Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Higher-density housing with heavy reliance on on-street parking - Close to Glenferrie Road shopping, dining and Swinburne University | Site not subject to third-party connection request when assessed | In service |  |
| 8 | Opp 33 Henry St Hawthorn 3122 | City of Boroondara | Voltage drop issues identified to add any load. High circuit demand (140kW) Substation: MALMSBURY-AUBURN Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Higher-density residential pocket with flats and terraces - Within reach of Burwood Road retail and train services | Site not subject to third-party connection request when assessed | In service |  |
| 9 | Adj 1 Smart St Hawthorn 3122 | City of Boroondara | Up to 50amps supply determined to be available. Single port charger connected – will not exceed limit Substation: SMART-ELGIN Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Within the Hawthorn activity area near Glenferrie Road - Student and staff population from nearby Swinburne University | Site not subject to third-party connection request when assessed | In service |  |
| 10 | 6 Hepburn St Hawthorn 3122 | City of Boroondara | Voltage drop issues identified to add any load. High circuit demand (184kW) Substation: HEPBURN-BURWOOD Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Dense residential street with high on-street parking demand - Near Glenferrie Road retail, tram and train services | Site not subject to third-party connection request when assessed | In service |  |
| 11 | 25 Queens Ave Hawthorn 3122 | City of Boroondara | Supply available – no network constraints Substation: QUEENS 1- HENRY (R) Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Mix of apartments and townhouses - Close to Burwood Road shops and public transport | Site not subject to third-party connection request when assessed | In service |  |
| 12 | Opp 15 Lovell St Hawthorn East 3123 | City of Boroondara | Voltage drop issues identified to add any load. High circuit demand (161kW) Substation: HALL-TOORONGA Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to Auburn Road shops and Camberwell Junction - Established residential street with high on-street parking use | Site not subject to third-party connection request when assessed | In service |  |
| 13 | 1 Wills St Hawthorn East 3123 | City of Boroondara | Voltage drop issues identified to add any load. High circuit demand (140kW) Substation: RIVERSDALE 480 - WILLS Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to Auburn Village shopping strip - Residential catchment with limited off-street parking | Site not subject to third-party connection request when assessed | In service |  |
| 14 | Opp 15 Constance St Hawthorn East 3123 | City of Boroondara | Voltage drop issues identified to add any load. Very high circuit demand (193kW) Substation: WISEMAN-TOORONGA Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Near Camberwell Junction retail and dining - Residential street with high on-street parking use | Site not subject to third-party connection request when assessed | In service |  |
| 15 | Opp 26 Hunter Rd Camberwell 3124 | City of Boroondara | Supply available – no network constraints Substation: HUNTER-LYNDEN Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to sporting facilities - Near Camberwell Junction, Camberwell Market and train station | Site not subject to third-party connection request when assessed | In service |  |
| 16 | Opp 11 Vears Rd Ashburton 3147 | City of Boroondara | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to sporting facilities - Near Ashburton village shops on High Street | Site not subject to third-party connection request when assessed |  | In service |
| 17 | 1A Lalla St Kew 3101 | City of Boroondara | Voltage drop and capacity issues identified to add any load. Dual port charger connected which will provide learnings as this equates to 63amps Substation: FLORENCE-PARKHILL Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 17 sites | - CPU selected - Close to football ground and bowls club - Serves visitors to local reserves and sports grounds | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 18 | 28 Gillies St Rochester 3561 | Campaspe Shire Council | Supply available – no network constraints Substation: GILLIES-MACKAY 2 Trans 1 | - Regional - Proactively contacted by council, established EV processes - Total 5 sites | - CPU selected - Located in Rochester’s main shopping street near the supermarket, shops and services - There are no existing EV chargers between Bendigo and Echuca - Provides a charging option for residents and people passing through town | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 19 | Opp 280 Hare St Echuca 3564 | Campaspe Shire Council | Voltage drop issues identified to add any load. Substation: HEYGARTH-HARE Trans 1 | - Regional - Proactively contacted by council, established EV processes - Total 5 sites | - CPU selected - Situated between the Port and main shopping precinct - Close to shops, restaurants and tourist attractions. - Short, easy walk into town. | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 20 | Opp 4 Percy St Echuca 3564 | Campaspe Shire Council | Supply available – no network constraints Substation: PERCY - ANNESLEY P3 Trans 1 | - Regional - Proactively contacted by council, established EV processes - Total 5 sites | - CPU selected - Located adjacent to the popular supermarket carpark - Close to shops, restaurants, tourist attractions, community facilities and the train station - Short, easy walk into town | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 21 | 105 Allan St Kyabram 3620 | Campaspe Shire Council | Supply available – no network constraints Substation: LAKE-ALLAN KYM 2 Trans 1 | - Regional - Proactively contacted by council, established EV processes - Total 5 sites | - CPU selected - Main-street location close to shops, cafés and services - Service town for the surrounding farming district | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 22 | 27 Moora Rd Rushworth 3612 | Campaspe Shire Council | Supply available – no network constraints Substation: MOORA-STANHOPE RUSH Trans 1 | - Regional - Proactively contacted by council, established EV processes - Total 5 sites | - CPU selected - Historic goldfields town serving visitors to Waranga Basin and nearby forest - Fills a public-charging gap in a small rural community | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 23 | 2 Montrose St Apollo Bay 3233 | Colac Otway Shire | Supply available – no network constraints (north circuit) Substation: WHELAN PASCOE 8E Trans 1 | - Regional - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - CPU selected - Great Ocean Road destination with high seasonal visitor numbers - Walkable to the foreshore, shops and cafés - Strong local campaign has asked for more charging options | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 24 | 11 Gallipoli Pde Apollo Bay 3233 | Colac Otway Shire | Supply available – no network constraints Substation: PENGILLEY COSTIN 8 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 7 sites | - Council selected - Close to school and medical centre - Supports EV drivers touring the Great Ocean Road - Strong local campaign has asked for more charging options | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 25 | 6 Station St Forrest 3236 | Colac Otway Shire | Voltage drop issues to add any load. Up to 25amps supply determined to be available. Dual port charger connected which will provide learnings as this equates to 63amps Substation: STATION P6 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 7 sites | - Council selected - Gateway to Otway mountain-bike trails and Lake Elizabeth - Visitor township with brewery, cafés and accommodation - Few public charging options between Colac and Apollo Bay | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 26 | 11 Old Beech Forest Rd Gellibrand 3239 | Colac Otway Shire | Circuit cables unknown. Unable to complete network assessment Substation: GELLIBRAND 231E Trans 1 | - Regional - Strong engagement and alignment across the council - Total 7 sites | - Council selected - Otway hinterland village on routes to forest and waterfall attractions - Near the Old Beechy Rail Trail and general store | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 27 | 42-44 Main St Birregurra 3242 | Colac Otway Shire | Cable capacity and voltage drop issues identified to add any load Substation: BIRREGURRA 55A Trans 1 | - Regional - Strong engagement and alignment across the council - Total 7 sites | - Council selected - Main street of a destination dining town, home to the restaurant Brae - Popular day-trip stop between Colac and the Otways | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 28 | Colac Station/Gellibrand St Colac 3250 | Colac Otway Shire | Supply available – no network constraints Substation: RAE-AMEZDROZ Trans 1 | - Regional - Strong engagement and alignment across the council - Total 7 sites | - Council selected - Adjacent to Colac railway station, supporting V/Line commuters - Close to the Colac town centre and Princes Highway | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 29 | 78 Main St Beeac 3251 | Colac Otway Shire | Voltage drop issues to add any load. Up to 7amps supply determined to be available. Dual port charger connected which will provide learnings as this equates to 63amps Substation: BEEAC P154 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 7 sites | - Council selected - Main-street location serving the local farming community - Tests charging demand in a low-density rural setting | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 30 | 26 Lewis St Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Council selected - Close to Frankston city centre shops, services and train station - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 31 | 15 Sheridan Ave Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Council selected - Residential catchment with access to local shops and parks - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 32 | 34 Willis St Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Council selected - Within the Frankston metropolitan activity centre catchment - Access to retail, health and education services - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 33 | 4 Clovelly Pde Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Council selected - Coastal residential area close to the Frankston foreshore - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 34 | 6 Royle St Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Council selected - Close to Frankston city centre and the waterfront - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 35 | 46 High St Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Council selected - Close to recreation areas - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 36 | 94 William St Frankston 3199 | Frankston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Highly supportive officers championed the trial, but achieving broader internal buy-in is taking considerable time - Total 7 sites | - Community selected - Close to Frankston city centre retail and public transport - Few existing charging options for Frankston’s population | Site not subject to third-party connection request when assessed | Waiting on council approval to commence community engagement |  |
| 37 | 85 Bendigo Ave Bentleigh 3204 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Near the Bentleigh activity centre on Centre Road and Bentleigh station - EV uptake is growing quickly and there are few existing public charging options | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 38 | 2A Gardeners Rd Bentleigh East 3165 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - CPU selected - Residential area near local reserves and schools - Situated adjacent to the Moorabbin Hospital and community health services | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 39 | King George Reserve, near 1st oval Bentleigh East 3165 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Community selected - Adjacent to sports ovals with regular weekend and evening use - Popular community sporting and recreation facilities | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 40 | Opp 61 Malane St Ormond 3204 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Close to Ormond station and North Road shops - Next to a popular park and sporting grounds - EV uptake is growing quickly in the area | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 41 | 125 Leila Rd Carnegie 3163 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Within the Carnegie–Ormond catchment, close to shops and train stations - Outside a park, bowls club and velodrome | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 42 | 10 Park Cres Caulfield North 3161 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - CPU selected - Outside Caulfield Park - This is a popular recreation area in a suburb that growing in population and density | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 43 | Lucan St (opp Woolies metro) Caulfield North 3161 | Glen Eira City Council | In CitiPower network. Voltage drop and capacity issues to add any load. Substation: NORWOOD-ORRONG Trans 2 | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Opposite a supermarket, supporting top-up charging while shopping - Close to local shops and cafés | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 44 | 17 Brooklyn Ave Caulfield South 3162 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Near Hawthorn Road and Glen Huntly Road shopping strips - Situated in a popular recreation precinct with several football ovals, a bowls club, tennis courts and a playground | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 45 | 12 Carre St Elsternwick 3185 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Close to Elsternwick station and Glen Huntly Road shopping and dining - Dense population with apartments opposite | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 46 | 66 Orrong Rd Elsternwick 3185 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Near Elsternwick village and Rippon Lea Estate - Busy area with a rapidly increasing EV uptake | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 47 | 26 Seymour Rd Elsternwick 3185 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Residential street within walking distance of Elsternwick village and station - Outside a popular local park - Opposite several older low rise apartment buildings with little opportunity for private charging | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 48 | Opp 19 Huntly St Glen Huntly 3163 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - Council selected - Near Glen Huntly Road shops and Glen Huntly station - Located outside a row of townhouses in a street with older apartment buildings | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 49 | 31 Murrumbeena Rd Murrumbeena 3163 | Glen Eira City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 13 sites | - CPU selected - Close to Murrumbeena station and village shops - Situated directly outside the bowls club - Older apartments and units in the area | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 50 | 7 Cardwell St Elmore 3558 | City of Greater Bendigo | Voltage drop and cable capacity issues identified to add any load. Very high circuit demand Substation: MITCHIE-CARDWELL P3 Trans 1 | - Regional - Highly supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 5 sites | - Council selected - Small town on the Northern Highway - Host of the Elmore Field Days, a major annual agricultural event - Situated outside a motel - A local community progress associated advocated for the charger to council - No existing charging options in the area | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 51 | 49 Reservoir Rd Strathdale 3550 | City of Greater Bendigo | Supply available – no network constraints Substation: RESERVOIR AVIARY 8 Trans 1 | - Regional - Highly supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 5 sites | - Residential suburb close to Strathdale Park sporting fields, playground and community hall - Near Kennington Reservoir walking and cycling trails and picnic areas - Short trip to Strath Village shopping centre, one of Bendigo’s busiest | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 52 | 18 Scott St White Hills 3550 | City of Greater Bendigo | Supply available – no network constraints Substation: PRIEST SCOTT 4E Trans 1 | - Regional - Highly supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 5 sites | - CPU selected - Residential suburb on Bendigo's northern edge, near local shops and parks | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 53 | Church St Eaglehawk 3556 | City of Greater Bendigo | Supply available – no network constraints Substation: VICTORIA HIGH 10 Trans 1 | - Regional - Highly supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 5 sites | - Council selected - Historic township centre with shops and heritage attractions | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 54 | Creek St Nth Opp mine Bendigo 3550 | City of Greater Bendigo | Supply available – no network constraints Substation: VIOLET HIGH 2 Trans 1 | - Regional - Highly supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 5 sites | - Council selected - Opposite tourist attraction - Close to Bendigo city-centre tourism, dining and services | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 55 | 126 Wilson St Horsham 3400 | Horsham Rural City Council | Supply available – no network constraints Substation: WILSON GARDENIA 7 Trans 1 | - Regional - Strong commitment across all levels enabled effective engagement and delivery - Total 1 site | - Council selected - Located in central Horsham - the main service centre for the Wimmera - Supports Western Highway travel between Melbourne and Adelaide - Close to the shopping centre, racetrack and skate park | Site not subject to third-party connection request when assessed | In service |  |
| 56 | 151 Osborne Ave Clayton South 3169 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - CPU selected - Mixed residential and employment area with daytime demand - Close to a popular local shopping strip | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 57 | 1 Grange Rd Cheltenham 3192 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - CPU selected - Close to the Moorabbin airport, museum, local cafe and industrial precinct | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 58 | 28 Florence St Mentone 3194 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - Council selected - Close to Mentone station, shops and beach - Popular local precinct with limited existing charging options | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 59 | 7 Horscroft Pl Moorabbin 3189 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - Council selected - Near the Moorabbin civic precinct, train station and Nepean Highway - Growth precinct with new apartment buildings - More high-density development planned in the near future | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 60 | Opp 3 Friendship Sq Cheltenham 3192 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - Council selected - Within the Charman Road shopping precinct near Cheltenham station - Next to older apartment buildings - No charging options in the direct vicinity | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 61 | 1148 Nepean Hwy Highett 3190 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - CPU selected - Major arterial location with high passing traffic - Near Highett station and shops - Outside three large apartment buildings | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 62 | Stanley Ave/Station St Cheltenham 3192 | Kingston City Council | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan - Officer-level support required broader management and cross-department alignment - Processes needed to be adapted or developed as the engagement progressed - Total 7 sites | - Council selected - Close to Cheltenham station, supporting commuter charging - Lots of shops and dining options in close proximity | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 63 | Opp 28 Young St Bacchus Marsh 3340 | Moorabool Shire Council | Supply available – no network constraints Substation: LERDERDERG - YOUNG Trans 1 | - Regional - Strong engagement and alignment across the council - Total 5 sites | - Council selected - Close to Bacchus Marsh Main Street shops and services - Growing commuter town on the Western Freeway | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 64 | 27 Graham St Bacchus Marsh 3340 | Moorabool Shire Council | Supply available – no network constraints Substation: GRAHAM-PILMER Trans 1 | - Regional - Strong engagement and alignment across the council - Total 5 sites | - Council selected - Within the Bacchus Marsh town-centre catchment | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 65 | 87 Steiglitz St Ballan 3342 | Moorabool Shire Council | Supply available – no network constraints Substation: EDOLS 8 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 5 sites | - Council selected - Main-street location close to cafés and shops - Convenient stop for Western Freeway travellers - Limited existing public charging options | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 66 | 17 Stead St Ballan 3342 | Moorabool Shire Council | Supply available – no network constraints (south circuit) Substation: EDOLS 8 Trans 1 *same substation as site #65 | - Regional - Strong engagement and alignment across the council - Total 5 sites | - Council selected - Residential area near the Ballan town centre - Limited existing public charging options | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 67 | 35 Martin St Blackwood 3458 | Moorabool Shire Council | Supply available – no network constraints Substation: MARTIN ST 7 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 5 sites | - Council selected - Historic goldfields village and gateway to Wombat State Forest - Popular visitor destination with gardens and walking trails - No existing charging options in the town | Site not subject to third-party connection request when assessed | Installed, not in service |  |
| 68 | 44 Hotham Rd Sorrento 3943 | Mornington Peninsula Shire | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan – coastal - Supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 6 sites | - Council selected - Coastal tourism destination with strong summer peaks - Near Sorrento shops and the Sorrento–Queenscliff ferry - Outside the football ground, bowls club, tennis courts and netball club | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 69 | 157 Marine Drive Safety Beach 3936 | Mornington Peninsula Shire | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan – coastal - Supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 6 sites | - Council selected - Foreshore location popular with beachgoers - Near Safety Beach marina and local shops - Outside the popular caravan park/camping ground | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 70 | 29 Hurley Crt Balnarring 3926 | Mornington Peninsula Shire | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan – coastal - Supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 6 sites | - Council selected - Near Balnarring village shops - Coastal hinterland township with holiday visitors - No existing charging options in Balnarring | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 71 | 87 Byrnes Rd Shoreham 3916 | Mornington Peninsula Shire | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan – coastal - Supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 6 sites | - Council selected - Small village close to Peninsula beaches and wineries - Local community facilities - No existing public charging options | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 72 | 23 Marine Drive Safety Beach 3936 | Mornington Peninsula Shire | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan – coastal - Supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 6 sites | - Council selected - Foreshore location near Safety Beach shops and boat ramp - Highly trafficked location – particularly during peak tourist season | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 73 | 42 Lochiel Ave Mount Martha 3934 | Mornington Peninsula Shire | N/A for network constraint assessment. The site remains relevant to the trial for broader EV charging and demand-management learnings | - Metropolitan – coastal - Supportive officers championed the trial, but achieving broader internal buy-in took considerable time - Total 6 sites | - Council selected - Close to Mount Martha village shops and beach - Limited existing charging options in Mount Martha | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 74 | 51 Cramer St Warrnambool 3280 | Warrnambool City Council | Voltage drop and capacity issues identified to add >10amps. Dual port charger connected which will provide learnings as this equates to 63amps Substation: CRAMER NELSON 7 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 2 sites | - CPU selected - Regional city at the western end of the Great Ocean Road - Close to shops and services | Site not subject to third-party connection request when assessed | In service |  |
| 75 | 226 Lava St Warrnambool 3280 | Warrnambool City Council | Supply available – no network constraints Substation: HENNA LAVA P7 Trans 1 | - Regional - Strong engagement and alignment across the council - Total 2 sites | - CPU selected - Central Warrnambool near Liebig Street dining and retail - Major service centre for south-west Victoria | Site not subject to third-party connection request when assessed | In service |  |
| 76 | 36 Newry St Carlton North 3054 | City of Yarra | Voltage drop issues to add any load. Supply capacity (amps) available Substation: NEWRY ST Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Dense terrace housing with very limited off-street parking - Near Rathdowne Village shops and cafés | Site not subject to third-party connection request when assessed | In service |  |
| 77 | 74 Paterson St Princes Hill 3054 | City of Yarra | Supply available – no network constraints Substation: WILSON ST (ENC) Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Close to Princes Park sporting and recreation facilities - Near the University of Melbourne and Lygon Street | Site not subject to third-party connection request when assessed | In service |  |
| 78 | 268 George St Fitzroy 3065 | City of Yarra | Voltage drop and cable capacity issues identified to add any load. Very high circuit demand (249kW) Substation: GEORGE-ST DAVID Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Heritage terrace precinct with limited off-street parking - Close to Gertrude and Brunswick Street dining and retail | Site not subject to third-party connection request when assessed | In service |  |
| 79 | 198 Napier St Fitzroy 3065 | City of Yarra | Voltage drop and cable capacity issues identified to add any load. Very high circuit demand (249kW) Substation: GEORGE-WEBB Trans 2 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near Brunswick Street and Gertrude Street retail and dining - High residential density | Site not subject to third-party connection request when assessed | In service |  |
| 80 | 131 Cambridge St Collingwood 3066 | City of Yarra | Supply available – no network constraints Substation: CAMBRIDGE-STANLEY Trans 2 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near Smith Street shopping and the Collingwood Yards arts precinct | Site not subject to third-party connection request when assessed | In service |  |
| 81 | 157 Gipps St Abbotsford 3067 | City of Yarra | Cable capacity issues identified to add any load. Single port charger connected which will provide learnings as this equates to 32amps Substation: GIPPS-PARK Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Mixed residential and employment precinct with apartments - Close to the Victoria Park sporting precinct | Site not subject to third-party connection request when assessed | In service |  |
| 82 | 19 Lithgow St Abbotsford 3067 | City of Yarra | Supply available – no network constraints Substation: LITHGOW-VICTORIA Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Within walking distance of Johnston Street and Victoria Park station | Site not subject to third-party connection request when assessed | In service |  |
| 83 | 10 Reeves St Clifton Hill 3068 | City of Yarra | Supply available – no network constraints Substation: ALEXANDRA 2-REEVES Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near Queens Parade shops and Clifton Hill station - High EV uptake with lots of terrace houses and apartments | Site not subject to third-party connection request when assessed | In service |  |
| 84 | 54 The Esplanade Clifton Hill 3068 | City of Yarra | Supply available – no network constraints Substation: SPENSLEY-CLIFTON Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near parkland and Clifton Hill village - High EV uptake with limited off street parking | Site not subject to third-party connection request when assessed | In service |  |
| 85 | 30A Rutland St Clifton Hill 3068 | City of Yarra | Cable capacity issues identified to add any load >5amps. Single port charger connected which will provide learnings as this equates to 32amps Substation: NOONE-GROOME Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near Clifton Hill station and Queens Parade village - High EV uptake with high density housing and little off street parking | Site not subject to third-party connection request when assessed | In service |  |
| 86 | 34 Fergie St Fitzroy North 3068 | City of Yarra | Voltage drop and cable capacity issues identified to add any load. Very high circuit demand (243kW) Substation: SCOTCHMER-ST GEORGES Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Close to Edinburgh Gardens and Brunswick Street North cafés - Street of terrace houses with the popular Edinburgh Gardens park nearby | Site not subject to third-party connection request when assessed | In service |  |
| 87 | 2 Mark St Fitzroy North 3068 | City of Yarra | Voltage drop and cable capacity issues identified to add any load. High circuit demand (174kW) Substation: FALCONER-MICHAEL Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Close to St Georges Road and Rae Street shops - Street of terrace houses close to the Edinburgh Gardens | Site not subject to third-party connection request when assessed | In service |  |
| 88 | 46 Noone St Clifton Hill 3068 | City of Yarra | Underground cable type/size unknown – assessed based on conservative assumption. Cable capacity issues identified to add any load >15amps Substation: ALEXANDRA-GOLD Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near Queens Parade village and Merri Creek parklands - High EV uptake in an area with terrace houses, apartments and little off-street parking | Site not subject to third-party connection request when assessed | In service |  |
| 89 | 193-205 McKean St Fitzroy North 3068 | City of Yarra | Cable capacity issues identified to add any load. Single port charger connected which will provide learnings as this equates to 32amps Substation: McKEAN-MICHAEL # Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Community selected - Close to the Clifton Hill shops and Edinburgh Gardens - Located outside the new community battery project - No off-street parking in the area | Site not subject to third-party connection request when assessed | In service |  |
| 90 | 67-76 Brighton St Richmond 3121 | City of Yarra | Cable capacity issues identified to add any load. Single port charger connected which will provide learnings as this equates to 32amps Substation: NORTHCOTE-BRIGHTON Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Dense terrace housing near Swan Street and Bridge Road - Residents in this area do not have access to off-street parking | Site not subject to third-party connection request when assessed | In service |  |
| 91 | 10 Stephenson St Cremorne 3121 | City of Yarra | Supply available – no network constraints Substation: DOVE-STEPHENSON (R) Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Within the Cremorne technology and creative employment hub - Near Swan Street retail and Richmond station - Highly trafficked area, particularly during the day | Site not subject to third-party connection request when assessed | In service |  |
| 92 | 26 Bendigo St Richmond 3121 | City of Yarra | Supply available to support single port charger (32amps max) Substation: DON-KHARTOUM Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Close to Swan Street shops and the sporting precinct - Location is surrounded by high density terrace houses, townhouses and apartments | Site not subject to third-party connection request when assessed | In service |  |
| 93 | 227 Highett St Richmond 3121 | City of Yarra | Voltage drop and cable capacity issues identified to add any load Substation: GLEADELL-BRIDGE Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Community selected - Near Bridge Road and Victoria Street shopping and dining - Outside a popular park and sporting area | Site not subject to third-party connection request when assessed | In service |  |
| 94 | 236 Smith St Collingwood 3066 | City of Yarra | Supply available to support dual port charger (63amps max) Substation: CAMBRIDGE-STANLEY Trans 2 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Community selected - On Smith Street, a busy retail and hospitality strip | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 95 | 22 Peel St Collingwood 3066 | City of Yarra | Supply available – no network constraints Substation: SMITH 172-OXFORD (R) Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - CPU selected - Near the Smith Street and Gertrude Street precincts - Lots of high density housing and office buildings | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 96 | 56 Easey St Collingwood 3066 | City of Yarra | Voltage drop and cable capacity issues identified to add any load Substation: BUDD-KEELE Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - CPU selected - Close to Smith Street retail and Collingwood's creative businesses - Area with terrace houses and little off-street parking | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 97 | 34 Barkley St Fitzroy North 3068 | City of Yarra | Voltage drop and cable capacity issues identified to add any load Substation: NICHOLSON-HOLDEN Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - CPU selected - Near St Georges Road and Edinburgh Gardens - Surrounding area has lots of terrace houses with little off street parking | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 98 | 40 Scotchmer St Fitzroy North 3068 | City of Yarra | Cable capacity issues identified to add any load. Dual port charger connected which will provide learnings as this equates to 63amps Substation: BATMAN-SCOTCHMER Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - CPU selected - Near Scotchmer Street village shops and cafés - Lots of terrace houses in the area and very little off-street parking | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 99 | 21 Stanley St Richmond 3121 | City of Yarra | Supply available – no network constraints Substation: CARROLL-SWAN Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - Council selected - Near Bridge Road and Church Street retail - Street has terrace houses with little off-street parking | Site not subject to third-party connection request when assessed | Under community engagement |  |
| 100 | 179 Clauscen St Fitzroy North 3068 | City of Yarra | Voltage drop and cable capacity issues identified to add any load. High circuit demand (183kW) Substation: CLAUSCEN-ST GEORGES Trans 1 | - Metropolitan - Highly engaged council with established EV processes and readiness to participate - Total 25 sites | - CPU selected - Dense residential area near local shops and parks - Limited off-street parking | Site not subject to third-party connection request when assessed | Under community engagement |  |